## Ark1
Subject | Author | Done by | Read?
Worksheets
3D Models | Haagh | 2017-10-28 | X | What | Working | Due Dates | Done
Scene (physical model) |  |  |  | ML | Oliver | 2017-11-23 | X
- Materials in UE4 |  |  |  | -Presentation |  | 2017-11-23
Scenario (rules) |  |  |  | CGP | Oliver | 2017-12-01 | X
Sockets | Atanas | 2017-10-28 |  | -Presentation | Oliver | 2017-12-01
IK Handles |  |  |  | UXD |  | 2017-11-21
C++ and BPs |  |  |  | -Presentation
Shader in UE4 | Oliver | 2017-11-10 | X
Proteus and networking
UX Stuff | Stjernholm | 2017-10-28 | X | Paper hand-in | Group | 2017-11-22
Context Study | Stjernholm + Atanas | 2017-10-28
|  |  |  | Final hand-in | Group | 2017-12-18
Article |  |  |  | Article Continued
Introduction | Oliver | 2017-10-28 | X | Should we have more intro | Oliver | 2017-11-20
- Motivation | Oliver | 2017-10-28 | X | - This could be about the robot itself
- Background | Oliver | 2017-10-28 | X | Robot Picture in Method |  | 2017-11-20
Methods |  |  |  | Results | Oliver | 2017-11-20
- Final System (interview too) | Atanas | 2017-11-10 |  | Operating Room Picture |  | 2017-11-20
- Test setup | Stjernholm | 2017-11-10 |  | Roles and Tasks Picture |  | 2017-11-20
- Materials | Nicklas | 2017-11-10 | X
- Procedure(s) | Nicklas | 2017-11-10 | X
Results (usability / expert) | Freddie | 2017-11-10
Conclusion
Extra Work
Introduction fix table | Nicklas | 2017-11-03 | X
Source on price of RAMIS | Oliver | 2017-11-03 | X
Include tools in Artefact model | Stjernholm | 2017-11-03 | X
Merge interviews and obs. | Freddie | 2017-11-03 | X
Interview conclusions | Freddie | 2017-11-03 | X
Add Johan's interview | Freddie | 2017-11-03 | X
Rewrite rules | Atanas | 2017-11-03 | X
Remake rules mindmap | Stjernholm | 2017-11-10 | X